## Work plan - high level
Forms | Content/types | Tenant, System, Project
Layout
Relationship
| Alerts & Notifications | integration with Outlook
Dashboards/Views | Projects | Filters,sort, group by etc.
| Systems: POC/demo/trainning VS. Proudction | Tow different views as their management is different
Infrastructure
Upgrade management
Executive reports | As what we have now in QB
General | All tables should be have the option to export to csv
All countries, and customer names should be in code names, real names should be exposed to permitted users
On any form, a form change update statement should appear stating the user name that made the last change and a full time stamp of the change date and time

## Workplan Tracker
Milestone | SubMilestone/Taks | SubMilestone/Taks | Task | Status | Milestone Completion Progress
Forms and Object design (data structure, layout, objects, functionalities) | Tenant form - POC |  |  | Done | 92.86%
| Tenant form - Customer |  |  | Done
| System form - POC/DEMO/Training |  |  | Done
| System fomr - customer/product |  |  | Done
| System Infrastructure tab/form (Roman) |  |  | Done
| Usage tab/form (Tenant and System) (Eyal) |  |  | Open
| Defining project types |  |  | Done
| Milestones and Task form |  |  | Done
| Project form - POC |  |  | Done
| Project form - Delivery new |  |  | Done
| Project form-Delivery-Upsell |  |  | Done
| Project form-Renewal-Standard |  |  | Done
| Project form-Renewal-Upsell |  |  | Done
| Project form-Renewal-Down Sell |  |  | Done
Operational design | POC/DEMO/Training system inventory – system creation |  |  | Done | 94.74%
| Production system inventory – system creation |  |  | Done
| Delivery projects handling – 16 workflows: | POC - 3 workflows | New requriements ONLY | Done
|  |  | Extension | Done
|  |  | End of POC | Done
|  | Delivery New | New requriements ONLY | Done
|  | Delivery Upsell | New requriements ONLY | Done
|  |  | Change request requirements ONLY | Done
|  |  | BOTH - New and Change request | Done
|  | Renewal - Standard | No requirements | Done
|  | Renewal - Upsell | Change request requirements ONLY | Done
|  |  | BOTH - New and Change request requirements | Done
|  |  | BOTH - New requriements + Standard | Done
|  |  | BOTH - Change request requirements + Standard | Done
|  |  | THREE - New and Change request + Standard | Done
|  |  | Standard ONLY - in case of price upsell only without configuration change | Done
|  | Renewal - Down sell | Change request requirements ONLY | Done
|  |  | BOTH - Change request requirements + Standard | Done
|  |  | Standard ONLY - in case of price down sell withotut configuration change | Done
| Notifications | System | Creation | Done
|  |  | Upgrdae | Done
|  | Warranty | Product | Done
|  |  | Infrastructure | Done
|  | End of POC |  | Done
|  | Tenant level | <TBD> | Open
| Alerts | System | Creation | Done
|  |  | Upgrdae | Done
|  | Warranty | Product | Done
|  |  | Infrastructure | Done
|  | End of POC |  | Done
|  | Projects |  | Done
|  | Tenant level | <TBD> | Open
| Emails Templates |  |  | Done
| Permissions high level | Project management |  | Done
|  | Support |  | Done
|  | Proffesional services |  | Done
|  | Procurement |  | Done
|  | Sales |  | Done
Dashboards design | POC/DEMO/Training inventory | Create |  | Done | 100%
|  | Delete |  | Done
|  | Edit |  | Done
|  | Assign to a POC |  | Done
|  | Setting system owner |  | Done
|  | Built-in sort/fiter by any column/group by |  | Done
|  | Defining columns and actions |  | Done
| Production system inventory | Create |  | Done
|  | Delete |  | Done
|  | Edit |  | Done
|  | Assign to a sell project (redirected from the project) |  | Done
|  | Defining columns and actions |  | Done
|  | Built-in sort/fiter by any column/group by |  | Done
| Projects | Built-in sort/fiter by any column/group by |  | Done
|  | Rows coloring by project status |  | Done
|  | Defininig default columns |  | Done
| Customer & POC Systems | Content - POC vs. Prodction |  | Done
|  | Built-in sort/fiter by any column/group by |  | Done
|  | Rows coloring by project status |  | Done
|  | Defininig default columns |  | Done
| Tenants (new) | Built-in sort/fiter by any column/group by |  | Done
|  | Rows coloring by project status |  | Done
|  | Defininig default columns |  | Done
| Infrastructure | Content |  | Done
|  | Defininig default columns |  | Done
|  | Warrnaties |  | Done
Upgrade Scheduler Management | Layout |  |  | Done | 80%
| Workflow |  |  | Done
| Stakeholders |  |  | Done
| Emails and notifications |  |  | Done
| Meeting with Inbar |  |  | Open
Conncetivity to Octopus |  | First review |  | Done | 66.67%
|  | Alex to provide an overview doucment |  | Done
|  | Understanding current situation |  | Open
Total |  |  |  |  | 94.19%

## Tenant form-POC
T
| 1. Sticky Title |  | TID T1234
| 2. Header |  | Tenant Type | Operational mode | Alert
|  |  | Editable - Pick list: Customer Penlink/Internal | Editable - Pick list: Active Access blocked Deleted | "POC period over due"
|  |  | Project Type | Project Name | Project ID | POC Start Date | POC End Date
|  |  | Read only - POC (constant - derived from current linked project | Read only - auto set once the tenant is allocated to the POC project | Read only - a link - auto set once the tenant is allocated to the POC project | Read only - derived from POC project | Read only - derived from POC project
|  |  | Account (end user) | Region | Country | State | Time Zone | Time Group
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - auto generated by Country-Time Zone lookup table/formula | Read only - auto generated by lookup table
|  |  | Hosting SID | Hosting System Operational status | Hosting System version
|  |  | Read only - Derived from the hosing system once the tenant is created and allocated to a system | Read only - Derived from the hosing system once the tenant is created and allocated to a system | Read only - Derived from the hosing system once the tenant is created and allocated to a system
3. Tabs
| Configuration | Hosting | Engagement circles | Usage | Documents
Configuration – default presented tab:
Editable – main object where we update the tenant configuration
We can use the current 3-dimensional table i.e. with the headers: core details, modules, AI, Additional features etc.
| Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
| Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
Hosting:
Read only grid/table that shows the basic information of the systems the tenant was defined at.
Default sort – from newest/latest/current system to the oldest
Columns:
Current system - true/false/check mark
SID (as a link)
Operational status
Machine number (e.g. p202)
Version Number
Hosting type – On prem/Cloud/Hybrid
URL – system URL
Performance tier – STANDARD/POWERED
VPN – yes/no
VPN type – e.g. Fortigate/Cisco/Palo Alto
IP restriction – yes/no
Platform – AWS/Azure
CSP – e.g. SELA/Ingram etc.
AWS Region – specific name list of AWS
Azure region – specific name list of Azure
Engagement circle
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Usage
TBD
Documents
A simple browse dialog box/form
4. Remarks
Editable grid
Including the option to set a reminder that creates a meeting/event in Outlook, based on date (calendar controller)
Supports record/line deletion, edit
First 3 columns are reads only and auto-generated upon each record creation containing the following:
Sequential record ID
Full time stamp – date and time. In general, the date and time will always presented according to the user geographical location
User name – the remark author
The rest of the columns:
Type – note/warranty/temporary change/permanent change/task: with the option to add more types to authorized users.
Remark content – free text, preferred rich text with bullets/numbering/bold etc.
Due date – a calendar controller
Event created (optional) – a check mark that is generated automatically to show that event indeed created.
5. POC Period
|  | POC Start Date | POC End Date
|  | Clendar | Calendar | Comment: Both dates derived automatically from the POC project ID, but can be editable to permitted users
6. Configuration history – last section
A read only grid
First 3 columns:
Record id - auto generated, auto sequential number
Full time stamp – auto generated, accordiing to the user time zone
Recorded by – SF user that changed the tenant configuration in the configuration tab above (date and time)
The rest of the columns – identical to the Configuration tab above (3 dimension table - all the configuration fields e.g. product, #licenses, webloc #users etc.)

## Tenant form-Customer
T
| 1. Sticky Title | TID T1234
| 2. Header | Tenant Type | License Number | Operational mode | Warranty status | Alert
|  | Editable - Pick list: Customer Penlink/Internal | Read only - Auto generated - A combind string compsed of <TID><SID><PID> - once a system AND a project are linked. If not, the valus should be Not set yet | Editable - Pick list: Active Access blocked Deleted | Read only - generated by a formula based on the warranty tab record statuses: Not set yet Under contract Out of contract | Auto generated - depends on the use case - several examples: No allocated system Warranty - need to renew (at least one warranty is in Expired status) Warranty - Not set yet (no warranty record has created AND already allocated to a system AND was handed over to Sales -based on Tasks list update)
|  | Project Type | Project Name | Project ID | Delivery Date
|  | Read only - POC (constant - derived from current linked project | Read only - auto set once the tenant is allocated to the POC project | Read only - a link - auto set once the tenant is allocated to the POC project | Read only - derived from delivery project
|  | Account (end user) | Region | Country | State | Time Zone | Time Group
|  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - auto generated by Country-Time Zone lookup table/formula | Read only - auto generated by lookup table
|  | Hosting SID | Hosting System Operational status | Hosting System version
|  | Read only - Derived from the hosing system once the tenant is created and allocated to a system | Read only - Derived from the hosing system once the tenant is created and allocated to a system | Read only - Derived from the hosing system once the tenant is created and allocated to a system
2. Header – multi columns contains the following fields grouped by category/subject:
| Field | Attribute | Value | Comment
| License# | Read only | Composed of PIDSIDTID | e.g P2292S1832T5645
| Tenant type | Editable | Customer or Penlink | Defualt- derived from opportunity. Delivery specialist can create an internal Tenant and add it to any system with Tenant type = Penlink
| Delivery date | Read only | Date (Calendar) | Date can be updated only in the Delivery project by authorized user only
| Operational status | Editable | Active | With indicator icons
Access blocked
Deleted
| Warranty status | Read only | Not set yet - default | Auto-set + icons.
Under contract
Out of contract
| SID | Read only |  | Derived from the systemàtenant list
| Current version | Read only |  | Derived from current system
| Delivery project ID | Read only |  | Derived from Projectàtenant list
| Delivery project Name | Read only |  | Derived from Project ID or Projectàtenant list
| Account | Read only |  | Derived from Project
| Opportunity ID/Name | Read only |  | Derived from Project
| Country | Read only |  | Derived from Project/Account
| Time zone | Read only |  | Auto-set based on country
| Time group | Read only |  | Auto-set based on lookup table
3. Tabs
| Configuration | Hosting | Engagement circles | Usage | Document
Configuration – default presented tab:
Editable – main object where we update the tenant configuration
We can use the current 3-dimensional table i.e. with the headers: core details, modules, AI, Additional features etc.
| Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
| Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
Hosting:
Read only grid/table that shows the basic information of the systems the tenant was defined at.
Default sort – from newest/latest/current system to the oldest
Columns:
Current system - true/false/check mark
SID
Hosting type – On prem/Cloud/Hybrid
URL – system URL
Performance tier – STANDARD/POWERED
VPN – yes/no
VPN type – e.g. Fortigate/Cisco/Palo Alto
IP restriction – yes/no
Platform – AWS/Azure
CSP – e.g. SELA/Ingram etc.
AWS Region – specific name list of AWS
Azure region – specific name list of Azure
Engagement circle
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Usage
TBD
Documents
A simple browse dialog box/form
4. Remarks
Editable grid
Including the option to set a reminder that creates a meeting/event in Outlook, based on date (calendar controller)
Supports record/line deletion, edit
First 3 columns are reads only and auto-generated upon each record creation containing the following:
Sequential record ID
Full time stamp – date and time. In general, the date and time will always presented according to the user geographical location
User name – the remark author
The rest of the columns:
Type – note/warranty/temporary change/permanent change/task: with the option to add more types to authorized users.
Remark content – free text, preferred rich text with bullets/numbering/bold etc.
Due date – a calendar controller
Event created (optional) – a check mark that is generated automatically to show that event indeed created.
5. Warranties
Editable grid
Warranty type should be derived from the project type – delivery, renewal or upsell
| Column/Field name | Attribute | Formula/value
| Warranty id | read only | sequential, auto generated
| First warranty | read only | auto generated, the first warranty should be marked
| Predecessor | editable | - A List of a combind strings, composed of Warranty ID and TID. The combined strings should be separated by semicolon - The items of the list can be selected from a pick-list of warrnty IDs. - The delivery specilst selects the item manually in the following manner using two pick-lists: (1)The first pick list: Tenant ID - default tenant to be selected is the current/existing tenat weher the warranty record is currently edited. (2)The second pick-list is the Warrnty ID. The list is auto-updated based on the selected tenant ID. The delivery specialist selects form it the relevant warranty ID as the predecessor - The two selections, the Tenant ID and the Warrnaty ID shoud be disaplyed as compbind string in the predecessor field. This method addresses tenants unfication
| Successor | read only | auto generated, derived from the predecessor column
| Account ID/End user ID (depends how it is implemented in SF) | read only | derived from the tenant
| Related project ID | editable | a pick list (name and ID) of all the projects related to that tenant
| Warranty type | read only | auto generated from the selected project type upon project ID/name – delivery/upsell/renewal. Could be located after the Warranty ID first column.
| Opportunity ID | read only | auto generated from the selected project
| Start date | editable | a calendar
| End date | editable | a calendar
| Duration | read only | auto generated as end date minus start date
| Days before expiration | read only | auto generated, as end date minus “TODAY()”
| Warranty status | Read only, auto generated, based on the start-end date fields: | “Not set yet” - populated ONLY if there is a Warranty ID AND start-end date fields are empty
“Planned” - with a future start date (i.e. TODAY() is smaller than start date)
“Valid” - TODAY() is between the start and end date range
“Pending” - end date is less than 90 days from TODAY()
“Renewed” - in case it has successor, or in other words, another warranty record set it as its predecessor
|  | Read only - manual update via a dedicated form for editing | “No warranty” or “Out of contract” – in a dedicated field in the warranty record form (e.g. a boolean field that says “No warranty” = Yes/Not)
| Alerts | read only | auto generated, need to figure out what exactly it shows |  | #REF!
| Remark | editable | free text
| Example: |  |  |  | free text
6. Configuration history – last section
A read only grid
First 3 columns:
Record id - auto generated, auto sequential number
Full time stamp – auto generated, accordiing to the user time zone
Recorded by – SF user that changed the tenant configuration in the configuration tab above (date and time)
The rest of the columns – identical to the Configuration tab above (3 dimension table - all the configuration fields e.g. product, #licenses, webloc #users etc.)
5. Configuration history – last section
A read only grid
First 3 columns:
Record id - auto generated, auto sequential number
Full time stamp – auto generated, accordiing to the user time zone
Recorded by – SF user that changed the tenant configuration in the configuration tab above (date and time)
The rest of the columns – identical to the Configuration tab above (3 dimension table - all the configuration fields e.g. product, #licenses, webloc #users etc.)

## System form-POC-Demo-Training
1. Sticky Title |  | SID S1050 | SID - is generated automatically in a sequential manner, when the system is copied/paste from the POC/DEMO/TRAINING pool to the POC project
2. Header |  | Purpose | Machine number | Availabilty status | Operational mode | Alerts
|  | Varies - see attributes table below | Read only | Read only: AVAILABLE/OCCUPIED | Pick list: On/Off/Access blocked/Service blocked/ Deleted | System has no tenants -auto generated, only if it is a deliverd sysetm and not in the prodction pool
|  | Product | Logo | #Tenants
|  | Tangles - pick list of product types |  | Integer - auto generated based on number of tenatns both active and not active - default is 0 when the system created
|  | URL | Cognito Region | Time Group | Time group alert
|  | Https://fsddfdf.com - free text | Pick list: NA/EU/APAC | Derived from OLDEST Tenant (read only) | Alert in case a new tenant is different from the current time group - autgenerated
Current Project
<List of associated projects>
| For POC/Training/Demo pool only: ---> | Used in Region | Occupation start date | Occupation end date
|  | Pick list: NA/EU/APAC | Calendar | Calendar
Field | Attribute | Value | Comment
Purpose | Read only | "POC" | In POC project should be read only and auto populated set when the sysetm is assigned to the POC project
| Editable - pick list | DEMO SUPPORT TRAINING POC AVAILABLE OBSOLETE | In POC/Training/Demo pool
Machine Number | Read only | As it was set in its creation | In POC project should be read only and auto populated set when the sysetm is assigned to the POC project
| Free text | Set in its creation e.g. p202 | In POC/Training/Demo pool
Availability status | Read only | AVAILABLE/OCCUPIED | Auto generated
Operational status | Editable - pick list | On | With indicator icons - all these values considered as active system
Off
Access blocked
Service blocked
|  | Deleted | If it is Deleted, it should not displayed in the active systems only in the dedicated Deleted system dashboard/report
|  | Canceled | If it is canceled, it should not displayed in the active systems only in the dedicated Canceled system dashboard/report
Alert |  | "System has no tenant(s)" | Three conditions: 1. The syetm is a delivery system 2. The system is not in the inventroy pool list 3. #Tenant == 0
Product | Editable - pick list | The list: Tangles/Tangles Light/Webloc/Weaver/Trapddor/Lynx/DataAPI
Logo | Read only | Icon | Per product
#Tenants | Read only | Integer | Auto generated based on number of active an inactive tenants as they appear in the Tenant tab
URL | Editable | Free text | without space as a restriction
Cognito region | Editable - pick list | Pick list: NA/EU/APAC
Time group | Read only |  | Auto-set dervied from oldest ACTIVE tenant geo location
Time group alert | Read only | "Tenant #<TID> does not belong to system time group" | Auto genereated in case one of the Tenants is not in the system time group
Current projects | Read only |  | Only in case the system is currently assinged to a POC project
For POC/Training/Demo pool only:
Field | Attribute | Value | Comment
Used in Region | Editable - pick list | Pick list: NA/EU/APAC
Occupation Start Date | Editable - Calendar | Date | In case it is assigned to a POC project, the poc period shoud overrite these fields
Occupation End Date | Editable - Calendar | Date
|  |  |  | P1 | T-R1; T-R2 | New - S1235
|  |  |  | P2 | T-R3 | S1235
|  | T-R1 |  | P3 | T-R4; T-R5 | S1235
T-R-2
T-R-#
3. TABS |  |  | Tenant | Infrastructure(should include: Hosting, access details, vpn etc.) | Version update | Usage | Configuration history | Documents
Configuration
| Live |  | Administrative | [5 empty] | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
|  | Actions | TID | Delivery PID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
Within POC period |  | Delete/Edit/Move(to a differnet system) - for permitted users only | T1 |  | Account1 |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  |  | T2 | [6 empty] | 12
|  |  | T3 | [6 empty] | 5
|  |  | T4 | [6 empty] | 8 | 2
|  | System configuration | [6 empty] | Sum | 53 |  | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | 2FA;SSO | Sum | Sum | Sum
Exceeded POC period - to generate alert | Over due | Delete/Edit/Move(to a differnet system) - for permitted users only | The same struture as Under conract but without the summary line - System config
| Infrastructure | See "System-Infrastructure" sheet
Dynamic form presentation
Eache category in a separated section
| Version update | Grid. Read only in grid mode.
With the option to add/edit a record. Delete - to authorized user (via the record form)
According to the following table structure
*Machine number column - need to elaborate about the disnction between a production sysetm and demo/poc system
Usage
Documents
Lower sections
4. Remarks
Editable grid
Including the option to set a reminder that creates a meeting/event in Outlook, based on date (calendar controller)
Supports record/line deletion, edit
First 3 columns are reads only and auto-generated upon each record creation containing the following:
Sequential record ID
Full time stamp – date and time. In general, the date and time will always presented according to the user geographical location
User name – the remark author
The rest of the columns:
Type – note/warranty/temporary change/permanent change/task: with the option to add more types to authorized users.
Remark content – free text, preferred rich text with bullets/numbering/bold etc.
Due date – a calendar controller
Event created (optional) – a check mark that is generated automatically to show that event indeed created.
Comment:Alert sholud be generated upon exceedng the end date
5. Configuration history – last section
A read only grid
First 3 columns:
Record id - auto generated, auto sequential number
Full time stamp – auto generated, accordiing to the user time zone
Recorded by – SF user that changed the tenant configuration in the configuration tab above (date and time)
The rest of the columns – identical to the Configuration tab above (3 dimension table - all the configuration fields e.g. product, #licenses, webloc #users etc.)
6. Owner
7. Purpose history – last section
Comments
| A read only grid | Auto updaet every time the purpose is changed
Basic columns columns:
| Purpose | POC/Demo etc
| PID | Relevant only for POC Purpose
| SID | Relevant only for POC Purpose
TID
| Project name | Relevant only for POC Purpose
| Project status | Relevant only for POC Purpose
| Account name | Relevant only for POC Purpose
Product
| Version | For the specific purpose period
Start date
End date
Add New Tenant
Release to POC/Demo/Training pool

## System form-Customer
1. Sticky Title |  |  | SID S1235
2. Header |  |  | Purpose | Product | Logo | #Tenants | Operational mode | Alerts
|  |  | Delivery (read only - set when the object created as a delivery system) | Tangles - pick list of product types |  | Integer - auto generated based on number of tenatns both active and not active - default is 0 when the system created | Pick list: On/Off/Access blocked/Service blocked/ Deleted | System has no tenants -auto generated, only if it is a deliverd sysetm and not in the prodction pool
|  |  | URL | Cognito Region | Time Group | Time group alert
|  |  | Https://fsddfdf.com - free text | Pick list: NA/EU/APAC | Derived from OLDEST Tenant (read only) | Alert in case a new tenant is different from the current time group - autgenerated
Linked Project
P1;P2;
|  | For Proudction Inventory only:---> | Destined/Designated Rgion | Prospect
|  |  | Pick list: NA/EU/APAC | Free text
Field | Attribute | Value | Comment
Purpose | Read only | "Delivery" | Auto set when the sysetm was created as a delviery system
Product | Editable - pick list | The list: Tangles/Tangles Light/Webloc/Weaver/Trapddor/Lynx/DataAPI
Logo | Read only | Icon | Per product
#Tenants | Read only | Integer | Auto generated based on number of active an inactive tenants as they appear in the Tenant tab
Operational status | Editable - pick list | On | With indicator icons - all these values considered as active system
Off
Access blocked
Service blocked
|  | Deleted | If it is Deleted, it should not displayed in the active systems only in the dedicated Deleted system dashboard/report
|  | Canceled | If it is canceled, it should not displayed in the active systems only in the dedicated Canceled system dashboard/report |  | T-R1
Alert |  | "System has no tenant(s)" | Three conditions: 1. The syetm is a delivery system 2. The system is not in the inventroy pool list 3. #Tenant == 0 |  | T-2
T-R3
URL | Editable | Free text | without space as a restriction |  | T-R-4
Cognito region | Editable - pick list | Pick list: NA/EU/APAC
Time group | Read only |  | Auto-set dervied from oldest ACTIVE tenant geo location
Time group alert | Read only | "Tenant #<TID> does not belong to system time group" | Auto genereated in case one of the Tenants is not in the system time group
Linked projects | Read only - List |  | Derived from all the projects the Tenants in the system are associated with
For Proudctio Inventory only:--->
Field | Attribute | Value | Comment
Destined/Designated Rgion | Editable | Pick list: NA/EU/APAC
Prospect | Editable - pick list | Free text
TBD
[5 empty] | Tenant Reqirments | New/Exisitng | Requested system
|  |  |  | P1 | T-R1; T-R2 | New | S1235
|  |  |  | P2 | T-R3 | Exsiting | S1235
|  | T-R1 |  | P3 | T-R4; T-R5 | Exsiting | S1238
T-R-2
T-R-#
3. TABS |  |  | Tenant | Infrastructure(should include: Hosting, access details, vpn etc.) | Version update | Usage | Configuration history | Documents
Configuration
| Under Contract | Administrative | [6 empty] | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
|  | Actions | TID | Delivery PID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
|  | Delete/Edit/Move(to a differnet system) - for permitted users only | T1 | P1 | Account1 |  |  |  | Tangles | 20 | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | 20 | 4 | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  |  | T2 | P1 | Account1 | [5 empty] | 12
|  |  | T3 | P2 | Account2 | [5 empty] | 5
|  |  | T4 | [7 empty] | 8 | 2
|  | System configuration | [7 empty] | Sum | 53 |  | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | Sum | 2FA;SSO | Sum
| Out of contract | Delete/Edit/Move(to a differnet system) - for permitted users only | The same struture as Under conract but without the summary line - System config
| Infrastructure | See "System-Infrastructure" sheet
Dynamic form presentation
Eache category in a separated section
| Version update | Grid. Read only in grid mode.
With the option to add/edit a record. Delete - to authorized user (via the record form)
According to the following table structure
*Machine number column - need to elaborate about the disnction between a production sysetm and demo/poc system
Usage
Documents
Lower sections
4. Remarks
Editable grid
Including the option to set a reminder that creates a meeting/event in Outlook, based on date (calendar controller)
Supports record/line deletion, edit
First 3 columns are reads only and auto-generated upon each record creation containing the following:
Sequential record ID
Full time stamp – date and time. In general, the date and time will always presented according to the user geographical location
User name – the remark author
The rest of the columns:
Type – note/warranty/temporary change/permanent change/task: with the option to add more types to authorized users.
Remark content – free text, preferred rich text with bullets/numbering/bold etc.
Due date – a calendar controller
Event created (optional) – a check mark that is generated automatically to show that event indeed created.
5. Configuration history – last section
A read only grid
First 3 columns:
Record id - auto generated, auto sequential number
Full time stamp – auto generated, accordiing to the user time zone
Recorded by – SF user that changed the tenant configuration in the configuration tab above (date and time)
The rest of the columns – identical to the Configuration tab above (3 dimension table - all the configuration fields e.g. product, #licenses, webloc #users etc.)
Add New Tenant
Move back to inventory

## System form-Infrastructure tab
System |  | Category | Sub-category | Item |  |  |  | Comments
| Infrastructure | Host | On prem | Server | Owner | Penlink/Customer/agent
[5 empty] | Type | <server U1/ U2/ U3..> | U
[5 empty] | Purpose | <Tangles host/storage/backup etc.>
Owner
Manufacturer
Model
Memory
CPU
Disk list
[6 empty] | Disk1 | <type/size>
[6 empty] | Disk2 | <type/size>
[6 empty] | Disk3 | <type/size>
…
Firmware
<Version>
Last date of update
|  |  |  | ESXi | ESXi
Version
Warranty
Intial warranty date
Start date
[7 empty] | End date | //with alert mechanism as with the server
[7 empty] | Status | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
Warranty
Type
Intial warranty date
Start date
[6 empty] | End date |  | //with alert mechanism as with the server
Contact details
Name
Email
Phone
Geographical address
[6 empty] | Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
[5 empty] | Configuration change history |  |  | //Grid with all the fields above
Comments
Cloud
[5 empty] | Platform |  |  | //Azure/AWS/Azure GOV etc.
CSP
[6 empty] | Name |  | //SELA/Ingram NZ/AutomateIT…
[6 empty] | Owner | <Penlink/Customer>
[6 empty] | Website |  | //Link to the CSP portal
Region
[5 empty] | Configuration change history |  |  | //Grid with all the fields above
Comments
Firewall
Type
[5 empty] | <Fortigate/Cisco…./WAF |  |  | //Includes all types of FW, no matter cloud or physical
[6 empty] | FortiGate Manager |  | //Conditional field - appears only if FortiGate is selected
Model
|  |  | Firmware |  |  |  |  | //Conditional field - appears only if physical FW is selected
| S1 |  |  |  | Version
[5 empty] | Autoupdate Active |  |  | // <Yes/No> - conditional field - appears only if physical FW is selected
Owner
<Penlik/customer/agent>
[6 empty] | Agent ID/name |  | //Conditional field - appears only if Agent s selected
Warranty
Type
Intial warranty date
Start date
[5 empty] | End date |  |  | //with alert mechanism as with the server
Contact details
Name
Email
Phone
Geographical address
Comments
|  | VM list | VM 1
Name <RDM>
[5 empty] | OS |  |  | //Win/linux
[5 empty] | Performance tier |  |  | / standard/powered
VM 2
Name <RDM>
OS
Performance tier
VM 3
..
..
|  | Network Access | VPN |  | Type
[6 empty] | <Fortigate/Cisco…./Open VPN |  | //W/O creds!, nor IP/Port - all in RDM
[7 empty] | Link to Open VPN | //Conditional field - appears only if Open VPN s selected
|  |  | IP Restriction |  | <Yes/No>
|  |  | External Interface |  | <Yes/No>
Maintenance
|  |  | History |  | <logs - grid type |  |  | // A grid with prediefined headres needs to be defined e.g. Mantainance type, Assgined engineer, date/time etc.
|  | Domains | Domain 1
Name
[5 empty] | Expiration date |  |  | //with alert mechanism as with the server including if date is missting
[6 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
SSl expiration date
Renewal Status
Domain 2
Name
[5 empty] | Related to | <Tangles url/TS>
[5 empty] | Expiration date |  |  | //with alert mechanism as with the server including if date is missting
[6 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
SSl expiration date
Renewal Status
Domain 3
..
..
Target site
TS 1
Name <RDM>
[5 empty] | Domain list |  |  | //List of domain names
[5 empty] | SSL List |  |  | //Add button from existing domain list + link to selected domain + report/grid of only TS domain list
VPS provider
[5 empty] | Expiration/renewal date |  |  | //with alert mechanism as with the server including if date is missting
[6 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
TS 2
Name <RDM>
Domain list
VPS provider
[5 empty] | Expiration/renewal date |  |  | //with alert mechanism as with the server including if date is missting
[6 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
TS 3
Name <RDM>
Domain list
VPS provider
Expiration/renewal date

## System form-Infrastructure (2)
Exiting Items in QB
|  | Ctegory list | Item Type
|  | Hardware | Server
Firewall
Firewall Kit
Laptop
Storage Server
FW Token
|  | Software | OpenVPN license
Windows Server Std 2019
VMware vSphere 7 Essentials Plus Kit
ESXi
|  | Certificate | SSL
|  | Domain | Domain
| Basic data for each item: | Field/Section | Sub field | Type/comment
|  | Basic details - mandatory | Reference | Pick-list Single Selection - a list of exsiting product type e.g. Tangles
|  |  | Category | Pick-list Single Selection
|  |  | Type | Pick-list Single Selection
|  |  | Identifer | Free text - S/N or any unique ID
|  |  | Owner | Pick-list Single Selection - Penlink/Agent/Customer
|  | Warranty | Initial Warranty Start Date | Calendar/Date | Alerts Mechanism
|  |  | Current Warranty Start Date | Calendar/Date
|  |  | Current Warranty End Date | Calendar/Date
|  |  | Days before expiration | Auto generated - TODAY()-End date
|  |  | Renewal status | Auto generated - Not set yet, Planned, Valid, Expired, Manual updated - No warranty, Obsolete
|  | Warranty contact person | Name | Free text
|  |  | Email | Free text
|  |  | Phone | Free text
|  |  | Address | Free text
|  | Geo location |  | Free text
|  | Allocated systems |  | TBD - could be as today a grid with one pick-list field for SID
System |  | Category | Sub-category | Item | Sub-item | Properties/Parameter | Value/Sub-field | Value/Sub-field | Field type | Comments
| Infrastructure | Host | On prem | Server |  | Type | <server U1/ U2/ U3..> |  | Pick list single select + add item
[6 empty] | Purpose | <Tangles host/storage/backup etc.> |  | Pick list single select + add item
[6 empty] | Owner | Penlink/Customer/agent |  | Pick list single select + add item
[6 empty] | Manufacturer |  |  | Pick list single select + add item
[6 empty] | Model |  |  | Pick list single select + add item
[6 empty] | Memory |  |  | Pick list single select + add item
[6 empty] | CPU |  |  | Pick list single select + add item
[6 empty] | Disk <list> + add item | Disk1 (type/size) |  | Pick list single select + add item
[7 empty] | Disk2 (type/size) |  | Pick list single select + add item
[7 empty] | Disk3 (type/size) |  | Pick list single select + add item
[7 empty] | Disk4 (type/size) |  | Pick list single select + add item
[7 empty] | Disk5 (type/size) |  | Pick list single select + add item
Firmware
[7 empty] | Version |  | Pick list single select + add item
[7 empty] | Last date of update |  | Calendar/Date
Warranty
[7 empty] | Type |  | Pick list single select + add item
[7 empty] | Intial warranty date |  | Calendar/Date
[7 empty] | Start date |  | Calendar/Date
[7 empty] | End date |  | Calendar/Date | //with alert mechanism as with the server
[7 empty] | Contact details |  | Free text
[8 empty] | Name | Free text
[8 empty] | Email | Free text
[8 empty] | Phone | Free text
[8 empty] | Geographical address | Free text
[7 empty] | Status |  |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
[6 empty] | Configuration change history |  |  | Editbale grid with READ ONLY: Timestamp, Author | //Grid with all the fields above
[6 empty] | Comments |  |  | Editbale grid with READ ONLY: Timestamp, Author
[5 empty] | ESXi | Version
Warranty
[7 empty] | Intial warranty date |  | Calendar/Date
[7 empty] | Start date |  | Calendar/Date
[7 empty] | End date |  | Calendar/Date | //with alert mechanism as with the server
[7 empty] | Status (valid,expired/ pending/obsolete, etc.) |  | READ ONLY- auto generated with UI indicator | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
|  |  | Cloud | N/R
[6 empty] | Platform |  |  | Pick list single select + add item | //Azure/AWS/Azure GOV etc.
CSP
[7 empty] | Name |  | Pick list single select + add item | //SELA/Ingram NZ/AutomateIT…
[7 empty] | Owner |  | Pick list single select + add item
[7 empty] | Website |  | Pick list single select + add item | //Link to the CSP portal
[6 empty] | Region |  |  | Pick list single select + add item
[6 empty] | Configuration change history |  |  | Editbale grid with READ ONLY: Timestamp, Author | //Grid with all the fields above
[6 empty] | Comments |  |  | Editbale grid with READ ONLY: Timestamp, Author
|  | Firewall |  | Firewall
Type
[7 empty] | <Fortigate/Cisco…./WAF |  | Pick list single select + add item | //Includes all types of FW, no matter cloud or physical
[8 empty] | FortiGate Manager | Boolean - Yes/No | //Conditional field - appears only if FortiGate is selected
[6 empty] | Model |  |  | Pick list single select + add item
[6 empty] | Firmware |  |  |  | //Conditional field - appears only if physical FW is selected
| S1 | [5 empty] | Version |  | Pick list single select + add item
[7 empty] | Autoupdate Active |  | Boolean - Yes/No | // <Yes/No> - conditional field - appears only if physical FW is selected
Owner
[7 empty] | <Penlik/customer/agent> |  | Pick list single select + add item
[8 empty] | Agent ID/name | Pick list single select + add item | //Conditional field - appears only if Agent s selected
Warranty
[7 empty] | Type |  | Pick list single select + add item
[7 empty] | Intial warranty date |  | Calendar/Date
[7 empty] | Start date |  | Calendar/Date
[7 empty] | End date |  | Calendar/Date | //with alert mechanism as with the server
Contact details
[8 empty] | Name | Free text
[8 empty] | Email | Free text
[8 empty] | Phone | Free text
Geographical address
Comments
|  | VM list |  | VM 1
[6 empty] | Name <RDM> |  |  | Free text
[6 empty] | OS | //Win/linux |  | Pick list single select + add item
[6 empty] | Performance tier | / standard/powered |  | Pick list single select + add item
VM 2
[6 empty] | Name <RDM> |  |  | Free text
[6 empty] | OS |  |  | Pick list single select + add item
[6 empty] | Performance tier |  |  | Pick list single select + add item
VM 3
..
..
|  | Network Access |  | N/R |  | VPN | Yes/No | Type (if Yes selected) | Pick list single select + add item (<Fortigate/Cisco…./Open VPN)
[6 empty] | IP Restriction | <Yes/No> |  | Boolean - Yes/No |  |  | //W/O creds!, nor IP/Port - all in RDM
[6 empty] | External Interface | <Yes/No> |  | Boolean - Yes/No
[11 empty] | Link to Open VPN | //Conditional field - appears only if Open VPN s selected
|  | Maintenance (Histoy) |  | N/R
[6 empty] | <logs - grid type |  |  | Editbale grid with READ ONLY: Timestamp, Author | // A grid with prediefined headres needs to be defined e.g. Mantainance type, Assgined engineer, date/time etc.
|  | Domains |  | Domain 1
[6 empty] | Name |  |  | Free text
[6 empty] | Expiration date |  | //with alert mechanism as with the server including if date is missting | Calendar/Date
[7 empty] | Renewal Status | //Not set yet/Valid/Pending renewal/Expired/Obselete etc. | Auto generated - READ ONLY
[6 empty] | SSl expiration date |  |  | Calendar/Date
[7 empty] | Renewal Status |  | Auto generated - READ ONLY
Domain 2
Name
[6 empty] | Related to | <Tangles url/TS>
[6 empty] | Expiration date |  |  | //with alert mechanism as with the server including if date is missting
[7 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
SSl expiration date
Renewal Status
Domain 3
..
..
|  | Target site |  | TS 1
Name <RDM>
[6 empty] | Domain list |  |  | //List of domain names
[6 empty] | SSL List |  |  | //Add button from existing domain list + link to selected domain + report/grid of only TS domain list
VPS provider
[6 empty] | Expiration/renewal date |  |  | //with alert mechanism as with the server including if date is missting
[7 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
TS 2
Name <RDM>
Domain list
VPS provider
[6 empty] | Expiration/renewal date |  |  | //with alert mechanism as with the server including if date is missting
[7 empty] | Renewal Status |  | //Not set yet/Valid/Pending renewal/Expired/Obselete etc.
TS 3
Name <RDM>
Domain list
VPS provider
Expiration/renewal date
Inrastructure
General info tab
Rsources Tab
Remarks - grid
4. Remarks
Editable grid
Including the option to set a reminder that creates a meeting/event in Outlook, based on date (calendar controller)
Supports record/line deletion, edit
First 3 columns are reads only and auto-generated upon each record creation containing the following:
Sequential record ID
Full time stamp – date and time. In general, the date and time will always presented according to the user geographical location
User name – the remark author
The rest of the columns:
Type –TBD
Remark content – free text, preferred rich text with bullets/numbering/bold etc.
Due date – a calendar controller
Event created (optional) – a check mark that is generated automatically to show that event indeed created.
Add Item

## Project form - general
Milestones & Tasks: Template mapping/legend
| Project type | Sub type | #Situations/use cases | New Tenant requirments | Change req | Warranty extension | Hosting type of new tenant | Templates # | Requirements table
| POC | Free | 1 | Yes |  |  | N/R | 1 | A
Paid
| Delivery | New | 1 | Yes |  |  | All Cloud | 2 | A
[7 empty] | At leas one Server | 3
|  | Upsell | 2 |  | Yes |  |  |  | B
|  |  | 3 | Yes |  |  | N/R | 4 | A
|  |  | 4 | Yes | Yes |  | All Cloud | 2 | A & B
[7 empty] | At leas one Server | 3 | A&B
| Renewal | Standard | 1 |  |  | Yes | N/R | 5 | C
|  | Upsell | 2 |  | Yes | Yes | N/R | 6 | B - and might be C if a standard renewal was included
|  |  | 3 | Yes |  |  | All Cloud | 7 | A - and might be C if a standard renewal was included
[7 empty] | At leas one Server | 8 | A - and might be C if a standard renewal was included
|  |  | 4 | Yes | Yes | Yes | All Cloud | 7 | A&B - and might be C if a standard renewal was included
[6 empty] | Yes | At leas one Server | 8 | A&B - and might be C if a standard renewal was included
|  | Down sell | 5 |  | Yes | Yes | N/R | 6 | B - and might be C if a standard renewal was included
Requirements types:
A:
| Comments: | Requirment types to display - generated base on opportuntiy
In case the opportunity editor requests to add a new tenant to an EXISTING system, SF should automatically set the prodcut type of the tenant, in the Core Details configuration, as it is defined already in the system, as it cannot be changed
| New Tenant Requirements: |  |  |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Requirment ID | New System (Boolean) |  | SID (If not a new system) | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
|  | Yes/No |  |  | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
B:
Comments: | Requirment types to display - generated base on opportuntiy
In the opportunity level - in case of selecting an existing Tenat , SF should block the option to set a the opportunity editor will NOT be able to change the product type
For Upsell/Down sell
| Change request on existing tenant - FINAL CONFIGURATIOIN: |  |  |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Req ID | TID |  | SID | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
|  | T2 |  | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
C:
Standard renewal:
| Req ID | TID | SID
|  | T2 | S123

## Milestones and Tasks Template
Project type: POC
Template #1
# | Milestones | Tasks | Department | Resource
1 | Environment configuration | Verifying system requirments are clear | Projects | Moshe
|  | Verifying start and end date are clear | Projects | Moshe
2 | Environment assignment | System(s) assigned | Projects | Moshe
|  | System is ON | Projects | Moshe
|  | System(s) is ready for installation | Projects | Moshe
3 | Factory installation | Running software upgrade (if needed) | Projects | Moshe
|  | DB Deletion & Creation (if needed) | Projects | Moshe
|  | Creating End User License document | Projects | Moshe
|  | Configuring Tangles | Projects | Moshe
|  | Users creation | Projects | Moshe
|  | Running sanity tests | Projects | Moshe
|  | Going over check list and save file | Projects | Moshe
|  | Running ATP | Projects | Moshe
|  | Saving ATP report file | Projects | Moshe
|  | Saving system configuration files | Projects | Moshe
|  | Clean activity log | Projects | Moshe
4 | Version update | System - Update software version number and build | Projects | Moshe
|  | System - Upload ATP report file | Projects | Moshe
|  | System - Upload check list file | Projects | Moshe
|  | System - Upload configuration file | Projects | Moshe
5 | Project documents | Project - Upload end user license document | Projects | Moshe
|  | Project - Upload Lynx extension settings (when exists) | Projects | Moshe
6 | Sending End User License | Sending End User License to customer/sales | Projects | Moshe
7 | End of POC | POC completed | Projects | Moshe
Project type: DELIVERY
|  |  | Project sub type: 1. New 2. Upsell that includes new tenant (no matter if there is a change request or not) | [7 empty] | Project sub type: 1. Upsell
| Template #2 |  |  |  |  | Template #3 |  |  |  |  | Template #4
| Cloud |  |  |  |  | On-prem/Hybrid |  |  |  |  | Change Request only
# | SAAS - milestones | Tasks | Department | Resource | # | On Premise - milestones | Tasks | Department | Resource |  | # | On Premise - milestones | Tasks | Department | Resource
1 | Environment configuration | Verifying system requirments are clear | Projects | Moshe | 1 | Environment configuration | Verifying system requirments are clear | Projects | Moshe |  | 1 | Configuration changes | Activity 1 | Projects | Moshe
2 | Environment assignment | System(s) assigned | Projects | Moshe |  |  | Sending Deployment Prepare New Environment request | Projects | Moshe |  |  |  | Activity 2 | Projects | Moshe
|  | System is ON | Projects | Moshe | 2 | Hardware readiness | Server and firewall were ordered | Deployment | Roman |  |  |  | Activity 3 | Projects | Moshe
|  | System(s) is ready for installation | Projects | Moshe |  |  | Server and firewall arrived | Deployment | Roman
3 | Factory installation | Setting system time zone | Projects | Moshe |  |  | Environment is ready to continue with delivery process | Deployment | Roman
|  | Setting recovery policy | Projects | Moshe | 3 | Site preparations | Sending SOW to customer or Sales manager | Projects | Moshe
|  | Site 24x7 - Activate Alerts | Projects | Moshe | 4 | Environment assignment | System(s) assigned | Projects | Moshe
|  | Running software upgrade (if needed) | Projects | Moshe |  |  | System is ON | Projects | Moshe
|  | DB Deletion & Creation (if needed) | Projects | Moshe |  |  | System(s) is ready for installation | Projects | Moshe
|  | Creating End User License document | Projects | Moshe | 5 | Factory installation | Setting system time zone | Projects | Moshe
|  | Configuring Tangles | Projects | Moshe |  |  | Setting recovery policy | Projects | Moshe
|  | Users creation | Projects | Moshe |  |  | Site 24x7 - Activate Alerts | Projects | Moshe
|  | Running sanity tests | Projects | Moshe |  |  | Running software upgrade (if needed) | Projects | Moshe
|  | Going over check list and save file | Projects | Moshe |  |  | DB Deletion & Creation (if needed) | Projects | Moshe
|  | Running ATP | Projects | Moshe |  |  | Creating End User License document | Projects | Moshe
|  | Saving ATP report file | Projects | Moshe |  |  | Configuring Tangles | Projects | Moshe
|  | Saving system configuration files | Projects | Moshe |  |  | Users creation | Projects | Moshe
|  | Clean activity log | Projects | Moshe |  |  | Running sanity tests | Projects | Moshe
4 | Version update | System - Update software version number and build | Projects | Moshe |  |  | Going over check list and save file | Projects | Moshe
|  | System - Upload ATP report file | Projects | Moshe |  |  | Running ATP | Projects | Moshe
|  | System - Upload check list file | Projects | Moshe |  |  | Saving ATP report file | Projects | Moshe
|  | System - Upload configuration file | Projects | Moshe |  |  | Saving system configuration files | Projects | Moshe
5 | Project documents | Project - Upload end user license document | Projects | Moshe |  |  | Clean activity log | Projects | Moshe
|  | Project - Upload Lynx extension settings (when exists) | Projects | Moshe |  |  | Getting FW settings documents | Deployment | Roman
6 | Sending End User License | Sending End User License to customer/sales | Projects | Moshe | 6 | Factory Version update | System - Update software version number and build | Projects | Moshe
|  | Ask for warranty dates | Projects | Moshe |  |  | System - Upload ATP report file | Projects | Moshe
|  | Ask for Freshdesk account(s) details | Projects | Moshe |  |  | System - Upload check list file | Projects | Moshe
7 | Features obligations | Feature1 | R&D | Moshe |  |  | System - Upload configuration file | Projects | Moshe
|  | Feature 2 | R&D | Moshe | 7 | Factory Project documents | Project - Upload end user license document | Projects | Moshe
8 |  | Feature 3 | R&D | Moshe |  |  | Project - Upload Lynx extension settings (when exists) | Projects | Moshe
| R&D open issues | Issue 1 | R&D | Moshe |  |  | Project - Upload FW settings file | Projects | Moshe
|  | Issue 2 | R&D | Moshe | 8 | Shipment | Validating addressee details (address, contact etc.) | Projects | Moshe
|  | Issue 3 | R&D | Moshe |  |  | Preparing packing list | Projects | Moshe
[7 empty] | Preparing commercial invoice | Projects | Moshe
[7 empty] | Validating MSDS and Safty material documents | Projects | Moshe
[7 empty] | Validating hipping method (door-to-door vs. door-to-airport) | Projects | Moshe
[7 empty] | Ordering and coordination shipping with shipping agency | Projects | Moshe
[7 empty] | Verifying packing list content in server package | Projects | Moshe
[7 empty] | Server package(s) are silled with battery label | Projects | Moshe
[7 empty] | Server package(s) are silled with consignee detatils label | Projects | Moshe
[7 empty] | Server is ready for pickup | Projects | Moshe
[7 empty] | Receiving AWB and tracking number from shipping agnecy | Projects | Moshe
[7 empty] | Printing AWB and commercial invoice and packing list | Projects | Moshe
[7 empty] | Equipment was picked up | Projects | Moshe
[7 empty] | Sending customer/sales AWB, Commercial invoice and packing list | Projects | Moshe
[7 empty] | Update/validate with customer upon system arrival | Projects | Moshe
[7 empty] | Schedule with customer and deployment installation date and time | Project | Moshe
[5 empty] | 9 | On site installation | System - Update VPN connetivity details | Project | Moshe
[7 empty] | Verifing deployment has connectivity with the system | Project | Moshe
[7 empty] | Installing infrastructure (if needed) | Project | Moshe
[7 empty] | Running software upgrade (if needed) | Project | Moshe
[7 empty] | Veirying system configuration | Project | Moshe
[7 empty] | Running sanity tests | Project | Moshe
[7 empty] | Going over check list and save file | Project | Moshe
[7 empty] | Running ATP | Project | Moshe
[7 empty] | Saving ATP report file | Project | Moshe
[7 empty] | Saving system configuration files | Project | Moshe
[7 empty] | Clean activity log | Project | Moshe
[5 empty] | 10 | On site version update | System - Update software version number and build | Projects | Moshe
[7 empty] | System - Upload ATP report file | Projects | Moshe
[7 empty] | System - Upload check list file | Projects | Moshe
[7 empty] | System - Upload configuration file | Projects | Moshe
[5 empty] | 11 | On site project documents | System - Upload VPN client file with site IP address | Projects | Moshe
[5 empty] | 12 | Sending End User License | Sending End User License to customer/sales | Projects | Moshe
[7 empty] | Sending FW settings to customer/sales | Projects | Moshe
[5 empty] | 13 | SAT | SAT execution | Sales | <Opportunity owner>
[7 empty] | Ask for warranty dates | Projects | Moshe
[7 empty] | Ask for Freshdesk account(s) details | Projects | Moshe
[5 empty] | 14 | Features obligations | Feature1 | R&D | Moshe
[7 empty] | Feature 2 | R&D | Moshe
[7 empty] | Feature 3 | R&D | Moshe
[5 empty] | 15 | R&D open issues | Issue 1 | R&D | Moshe
[7 empty] | Issue 2 | R&D | Moshe
[7 empty] | Issue 3 | R&D | Moshe
Project type: Renewal
| Project sub type: 1. Standard |  |  |  |  | Project sub type: 1. Upsell (wihtout new tenant requirements) 2. Down sell |  |  |  | Project sub type: 1. Upsell (inlcuding new tenant requirments)
Template #5 | [5 empty] | Template #6 | [6 empty] | Template #7 |  |  |  |  | Template #8
[13 empty] | Cloud |  |  |  |  | On-prem/Hybrid
# | On Premise - milestones | Tasks | Department | Resource | # | On Premise - milestones | Tasks | Department | Resource
1 | License renewal | License renewed | Projects | Moshe | 1 | License renewal | License renewed | Projects | Moshe |  |  | # | SAAS - milestones | Tasks | Department | Resource | # | On Premise - milestones | Tasks | Department | Resource
[5 empty] | 2 | Configuration changes | Activity 1 | Projects | Moshe |  |  | 1 | License renewal | License renewed | Projects | Moshe | 1 | License renewal | License renewed | Projects | Moshe
[7 empty] | Activity 2 | Projects | Moshe |  |  | 2 | Environment configuration | Verifying system requirments are clear | Projects | Moshe | 2 | Environment configuration | Verifying system requirments are clear | Projects | Moshe
[7 empty] | Activity 3 | Projects | Moshe |  |  | 3 | Environment assignment | System(s) assigned | Projects | Moshe |  |  | Sending Deployment Prepare New Environment request | Projects | Moshe
[14 empty] | System is ON | Projects | Moshe | 3 | Hardware readiness | Server and firewall were ordered | Deployment | Roman
[14 empty] | System(s) is ready for installation | Projects | Moshe |  |  | Server and firewall arrived | Deployment | Roman
[12 empty] | 4 | Factory installation | Setting system time zone | Projects | Moshe |  |  | Environment is ready to continue with delivery process | Deployment | Roman
[14 empty] | Setting recovery policy | Projects | Moshe | 4 | Site preparations | Sending SOW to customer or Sales manager | Projects | Moshe
[14 empty] | Site 24x7 - Activate Alerts | Projects | Moshe | 5 | Environment assignment | System(s) assigned | Projects | Moshe
[14 empty] | Running software upgrade (if needed) | Projects | Moshe |  |  | System is ON | Projects | Moshe
[14 empty] | DB Deletion & Creation (if needed) | Projects | Moshe |  |  | System(s) is ready for installation | Projects | Moshe
[14 empty] | Creating End User License document | Projects | Moshe | 6 | Factory installation | Setting system time zone | Projects | Moshe
[14 empty] | Configuring Tangles | Projects | Moshe |  |  | Setting recovery policy | Projects | Moshe
[14 empty] | Users creation | Projects | Moshe |  |  | Site 24x7 - Activate Alerts | Projects | Moshe
[14 empty] | Running sanity tests | Projects | Moshe |  |  | Running software upgrade (if needed) | Projects | Moshe
[14 empty] | Going over check list and save file | Projects | Moshe |  |  | DB Deletion & Creation (if needed) | Projects | Moshe
[14 empty] | Running ATP | Projects | Moshe |  |  | Creating End User License document | Projects | Moshe
[14 empty] | Saving ATP report file | Projects | Moshe |  |  | Configuring Tangles | Projects | Moshe
[14 empty] | Saving system configuration files | Projects | Moshe |  |  | Users creation | Projects | Moshe
[14 empty] | Clean activity log | Projects | Moshe |  |  | Running sanity tests | Projects | Moshe
[12 empty] | 5 | Version update | System - Update software version number and build | Projects | Moshe |  |  | Going over check list and save file | Projects | Moshe
[14 empty] | System - Upload ATP report file | Projects | Moshe |  |  | Running ATP | Projects | Moshe
[14 empty] | System - Upload check list file | Projects | Moshe |  |  | Saving ATP report file | Projects | Moshe
[14 empty] | System - Upload configuration file | Projects | Moshe |  |  | Saving system configuration files | Projects | Moshe
[12 empty] | 6 | Project documents | Project - Upload end user license document | Projects | Moshe |  |  | Clean activity log | Projects | Moshe
[14 empty] | Project - Upload Lynx extension settings (when exists) | Projects | Moshe |  |  | Getting FW settings documents | Deployment | Roman
[12 empty] | 7 | Sending End User License | Sending End User License to customer/sales | Projects | Moshe | 7 | Factory Version update | System - Update software version number and build | Projects | Moshe
[14 empty] | Ask for warranty dates | Projects | Moshe |  |  | System - Upload ATP report file | Projects | Moshe
[14 empty] | Ask for Freshdesk account(s) details | Projects | Moshe |  |  | System - Upload check list file | Projects | Moshe
[12 empty] | 8 | Features obligations | Feature1 | R&D | Moshe |  |  | System - Upload configuration file | Projects | Moshe
[14 empty] | Feature 2 | R&D | Moshe | 8 | Factory Project documents | Project - Upload end user license document | Projects | Moshe
[12 empty] | 9 |  | Feature 3 | R&D | Moshe |  |  | Project - Upload Lynx extension settings (when exists) | Projects | Moshe
[13 empty] | R&D open issues | Issue 1 | R&D | Moshe |  |  | Project - Upload FW settings file | Projects | Moshe
[14 empty] | Issue 2 | R&D | Moshe | 9 | Shipment | Validating addressee details (address, contact etc.) | Projects | Moshe
[14 empty] | Issue 3 | R&D | Moshe |  |  | Preparing packing list | Projects | Moshe
[19 empty] | Preparing commercial invoice | Projects | Moshe
[19 empty] | Validating MSDS and Safty material documents | Projects | Moshe
[19 empty] | Validating hipping method (door-to-door vs. door-to-airport) | Projects | Moshe
[19 empty] | Ordering and coordination shipping with shipping agency | Projects | Moshe
[19 empty] | Verifying packing list content in server package | Projects | Moshe
[19 empty] | Server package(s) are silled with battery label | Projects | Moshe
[19 empty] | Server package(s) are silled with consignee detatils label | Projects | Moshe
[19 empty] | Server is ready for pickup | Projects | Moshe
[19 empty] | Receiving AWB and tracking number from shipping agnecy | Projects | Moshe
[19 empty] | Printing AWB and commercial invoice and packing list | Projects | Moshe
[19 empty] | Equipment was picked up | Projects | Moshe
[19 empty] | Sending customer/sales AWB, Commercial invoice and packing list | Projects | Moshe
[19 empty] | Update/validate with customer upon system arrival | Projects | Moshe
[19 empty] | Schedule with customer and deployment installation date and time | Project | Moshe
[17 empty] | 10 | On site installation | System - Update VPN connetivity details | Project | Moshe
[19 empty] | Verifing deployment has connectivity with the system | Project | Moshe
[19 empty] | Installing infrastructure (if needed) | Project | Moshe
[19 empty] | Running software upgrade (if needed) | Project | Moshe
[19 empty] | Veirying system configuration | Project | Moshe
[19 empty] | Running sanity tests | Project | Moshe
[19 empty] | Going over check list and save file | Project | Moshe
[19 empty] | Running ATP | Project | Moshe
[19 empty] | Saving ATP report file | Project | Moshe
[19 empty] | Saving system configuration files | Project | Moshe
[19 empty] | Clean activity log | Project | Moshe
[17 empty] | 11 | On site version update | System - Update software version number and build | Projects | Moshe
[19 empty] | System - Upload ATP report file | Projects | Moshe
[19 empty] | System - Upload check list file | Projects | Moshe
[19 empty] | System - Upload configuration file | Projects | Moshe
[17 empty] | 12 | On site project documents | System - Upload VPN client file with site IP address | Projects | Moshe
[17 empty] | 13 | Sending End User License | Sending End User License to customer/sales | Projects | Moshe
[19 empty] | Sending FW settings to customer/sales | Projects | Moshe
[17 empty] | 14 | SAT | SAT execution | Sales | <Opportunity owner>
[19 empty] | Ask for warranty dates | Projects | Moshe
[19 empty] | Ask for Freshdesk account(s) details | Projects | Moshe
[17 empty] | 15 | Features obligations | Feature1 | R&D | Moshe
[19 empty] | Feature 2 | R&D | Moshe
[19 empty] | Feature 3 | R&D | Moshe
[17 empty] | 16 | R&D open issues | Issue 1 | R&D | Moshe
[19 empty] | Issue 2 | R&D | Moshe
[19 empty] | Issue 3 | R&D | Moshe

## Project Form - POC
1. Sticky Title PID #1234 |  |  | PID P1235
2. Header |  |  | Project name | Project Type | Project sub type | Delivery date | Start Date | End Date | Project status | Current milestone
|  |  | Editable - derived from Opportunity | Read only - derived from opportuniy | Read only - derived from opportuniy | Editable - Date (Calendar) - derived from opportuniy | Editable - Calendar - derived from opportunity | Editable - Calendar - derived from opportunity | Read only - Live/Done - based on tasks completion | Read only - from milestone list | Project Alers
|  |  | Opportunity (name and ID) | Account (end user) | Region | Country | State |  | Time Zone | Time Group | Read only - auto generated base on predefined alerts: - POC end date overdue - Delivery/start date is missing - Delivery/start date overdue
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy |  | Read only - auto generated by Country-Time Zone lookup table/formula | Read only - auto generated by lookup table
|  |  | Deal/Sale owner | Report to - direct | Report to - level 2
|  |  | Read only - derived from opportuniy | Read only - derived from organization chart | Read only - derived from organization chart
Available actions:
|  |  | Cancel project | Cancelation reason - mandatory *
Must be filled in in case a projec is canceled
3. Tenat requirements
| New Tenant Requirements: | // Sales manager can ask a POC on existing customer's system In case of a request of an existing system, to allocate it automatically to the system & tenant tab once the project is created
|  |  |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Requirment ID | New System? (Boolean) | SID (If NOT a new system) | Hosting - pick list single select | Cloud Platfrom - pick list single select | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
| #1234 | Yes/No | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
| #1235 | Yes
| #1236 | No | S456
| Milestones | Tasks | Systems and Tenants | Engagement circles | Documents
4. TABS
Milestones
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a milestone
Can create a new milstone
|  | A milestones status can be either: | Open - none of its tasks was completed
In progress - at least one but not all its tasks is completed
Done - all its tasks are completed
An indicator icon should be right to the milestones status
A progress bar should be displayed based on number of completed tasks
Order of milestones can be editted by permitted user only
Actions to support:
|  | Add milestone | Either from existing list or a new one
|  | Reset milestones (and tasks) | Set back the origianl milestones and their tasks according to the tempalte
The requested table and its fields:
Tasks
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a task
A task can creae only via a milestone - in a milestone form
|  | A task status can be either: | Open - none of its tasks was completed
Done - all its tasks are completed
An indicator icon should be right to the task status
Task status is update manually - by permitted user
Taks order is based by milestones order
Should be displayed as groups of of milestones
An option to set a dead line - a calendar type
|  | An option to set a dead line reminder in days | how many days beofore the deadline to generate alert
Alert - auto generaed upon either: over due or deadline reminder
|  | Ticket opening idicator/indication | Only for POC end - a ticket should be opened once "POC ended" taks is set as done and indicator should appear next to the task
Actions to support:
|  | Add Task | Only via a milestone form in the milestones tabs
The requested table and its fields:
|  | End of POC: | Once all the tasks are set as DONE, the POC is officialy closed and the system should be released to the POC/DEMO/Training system pool and set as available
Systems and Tenants
Existing System
List of added system after allocating them to the project with their current Cofiguration
Defautlt - empty list
Adding a system is done manually by the Delivery sepcialist
System allocation form - There should be two options: 1. To open and select only only AVAILABLE POD/DEMO/Training systems list - copy/paste 2. To present and select only proudction system(s) that belong/in use by the current account of the project
Once the sysetm is allocated it appears on the Existing system list
|  | Administrative | [5 empty] | Environment |  | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | SID | PIDs (PID list) |  | Time group | Operational status | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Deallocate/Edit/Move(to a differnet system/project) - for permitted users only | S1234 | <all the PID the system is currently allocated to |  |  |  | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 38 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | DeallocateEdit/Move(to a differnet system/project) - for permitted users only | S1235 | <all the PID the system is currently allocated to | [5 empty] | 12
Exsisting Tenants
Tenant is added only on System form and only then it appears on the sysetm below
After the Delivery specialist added the system to the project and verify the system full configuration and confirm he can contineu and add the tenant
|  | Administrative | [6 empty] | Environment |  | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | TID | SID | Account | Country | Time group | Operational status | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T1 | S1234 | Account1 - the project account only |  |  |  | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T2 | S1235 | Account1 | [5 empty] | 12
Engagement circles
Read only - based on role list as now in QB
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Documents
Allocate a System

## Project Form-Delivery-New
1. Sticky Title PID #1234 |  |  | PID P1235
2. Header |  |  | Project name | Project Type | Project sub type | Delivery date | Warranty/Service period (months) | Project status | Current milestone | Project Alers
|  |  | Free text | Read only - derived from opportuniy | Read only - derived from opportuniy | Editable - Date (Calendar) - derived from opportuniy | Read only - derived from opportuniy | Read only - Live/Done - based on tasks completion | Read only - from milestone list | Read only - auto generated base on predefined alerts: - Deliveryt date is missing - Delivery overdue
|  |  | Opportunity (name and ID) | Account (end user) | Region | Country | State | Time Zone | Time Group
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - auto generated by Country-Time Zone lookup table/formula | Read only - auto generated by lookup table
|  |  | Deal/Sale owner | Report to - direct | Report to - level 2
|  |  | Read only - derived from opportuniy | Read only - derived from organization chart | Read only - derived from organization chart
Available actions:
|  |  | Cancel project | Cancelation reason - mandatory *
Must be filled in in case a projec is canceled
3. Tenat requirements
| New Tenant Requirements: | In case of a request of an existing system, to allocate it automatically to the system & tenant tab once the project is created
| New Tenant Requirements: | // Sales manager can ask a POC on existing customer's system |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Requirment ID | New System (Boolean) | SID (If not a new system) | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
|  | Yes/No | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
4. TABS | Milestones | Tasks | Systems and Tenants | Engagement circles | Documents
Milestones
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a milestone
Can create a new milstone
|  | A milestones status can be either: | Open - none of its tasks was completed
In progress - at least one but not all its tasks is completed
Done - all its tasks are completed
An indicator icon should be right to the milestones status
A progress bar should be displayed based on number of completed tasks
Order of milestones can be editted by permitted user only
Actions to support:
|  | Add milestone | Either from existing list or a new one
|  | Reset milestones (and tasks) | Set back the origianl milestones and their tasks according to the tempalte
The requested table and its fields:
Tasks
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a task
A task can creae only via a milestone - in a milestone form
|  | A task status can be either: | Open - none of its tasks was completed
Done - all its tasks are completed
An indicator icon should be right to the task status
Task status is update manually - by permitted user
Taks order is based by milestones order
Should be displayed as groups of of milestones
An option to set a dead line - a calendar type
|  | An option to set a dead line reminder in days | how many days beofore the deadline to generate alert
Alert - auto generaed upon either: over due or deadline reminder
|  | Ticket opening idicator/indication | Only for POC end - a ticket should be opened once "POC ended" taks is set as done and indicator should appear next to the task
Actions to support:
|  | Add Task | Only via a milestone form in the milestones tabs
The requested table and its fields:
Systems and Tenants
Existing System
List of added system after allocating them to the project with their current Cofiguration
Defautlt - empty list
Adding a system is done manually by the Delivery sepcialist
System allocation form - There should be two options: 1. To open and select only from Product systems list - cut/paste 2. To present and select only proudction system(s) that belong/in use by the current account of the project
Once the sysetm is allocated it appears on the Existing system list
|  | Administrative | [5 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | SID | PIDs (PID list) | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1234 | <all the PID the system is currently allocated to |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1235 | <all the PID the system is currently allocated to | [5 empty] | 12
Exsisting Tenants
Tenant is added only on System form and only then it appears on the sysetm below
After the Delivery specialist added the system to the project and verify the system full configuration and confirm he can contineu and add the tenant
|  | Administrative | [6 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | TID | SID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T1 | S1234 | Account1 - the project account only |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T2 | S1235 | Account1 | [5 empty] | 12
Engagement circles
Read only - based on role list as now in QB
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Documents
Allocate a System

## Project form-Delivery-Upsell
1. Sticky Title PID #1234 |  |  | PID P1235
2. Header |  |  | Project name | Project Type | Project sub type | Delivery date | Warranty/Service period (months) | Project status | Current milestone | Project Alers
|  |  | Free text | Read only - derived from opportuniy | Read only - derived from opportuniy | Editable - Date (Calendar) - derived from opportuniy | Read only - derived from opportuniy | Read only - Live/Done - based on tasks completion | Read only - from milestone list | Read only - auto generated base on predefined alerts: - Deliveryt date is missing - Delivery overdue
|  |  | Opportunity (name and ID) | Account (end user) | Region | Country | State | Time Zone | Time Group
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - auto generated by Country-Time Zone lookup table/formula | Read only - auto generated by lookup table
|  |  | Deal/Sale owner | Report to - direct | Report to - level 2
|  |  | Read only - derived from opportuniy | Read only - derived from organization chart | Read only - derived from organization chart
Available actions:
|  |  | Cancel project | Cancelation reason - mandatory *
Must be filled in in case a projec is canceled
3. Tenat requirements
Comments: | Requirment types to display - generated base on opportuntiy | System and Teant Tab auto-update | System allocation comments
| The following requirement combinations can be: 1. New requriements ONLY 2. Change request requirements ONLY 3. BOTH - New and Change request Maximum 2 types of requirement tables | The selected tenants and their systems for change request requirment, should automatically appear/added to the System and Tenant tab when the Project is created | Change request requirements: to allocate the relevant systems & Tenant automatically to the system & tenant tab once the project is created New Tenant Requirement : In case of a request of an existing system, to allocate it automatically to the system & tenant tab once the project is created
| New Tenant Requirements: | // Sales manager can ask a POC on existing customer's system |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Requirment ID | New System (Boolean) | SID (If not a new system) | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
|  | Yes/No | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
| Change request on existing tenant - FINAL CONFIGURATIOIN: |  |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Req ID | TID | SID | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
| Requirment ID | T3 | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
| T3 | S123
4. TABS | Milestones | Tasks | Systems and Tenants | Engagement circles | Documents
Milestones
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a milestone
Can create a new milstone
|  | A milestones status can be either: | Open - none of its tasks was completed
In progress - at least one but not all its tasks is completed
Done - all its tasks are completed
An indicator icon should be right to the milestones status
A progress bar should be displayed based on number of completed tasks
Order of milestones can be editted by permitted user only
Actions to support:
|  | Add milestone | Either from existing list or a new one
|  | Reset milestones (and tasks) | Set back the origianl milestones and their tasks according to the tempalte
The requested table and its fields:
Tasks
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a task
A task can creae only via a milestone - in a milestone form
|  | A task status can be either: | Open - none of its tasks was completed
Done - all its tasks are completed
An indicator icon should be right to the task status
Task status is update manually - by permitted user
Taks order is based by milestones order
Should be displayed as groups of of milestones
An option to set a dead line - a calendar type
|  | An option to set a dead line reminder in days | how many days beofore the deadline to generate alert
Alert - auto generaed upon either: over due or deadline reminder
|  | Ticket opening idicator/indication | Only for POC end - a ticket should be opened once "POC ended" taks is set as done and indicator should appear next to the task
Actions to support:
|  | Add Task | Only via a milestone form in the milestones tabs
The requested table and its fields:
Systems and Tenants
Existing System
List of added system after allocating them to the project with their current Cofiguration
Defautlt - empty list
Adding a system is done manually by the Delivery sepcialist
System allocation form - There should be two options: 1. To open and select only only Available POD/DEMO/Training systems list 2. To present and select only proudction system(s) that belong/in use by the current account of the project
Once the sysetm is allocated it appears on the Existing system list
|  | Administrative | [5 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | SID | PIDs (PID list) | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1234 | <all the PID the system is currently allocated to |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1235 | <all the PID the system is currently allocated to | [5 empty] | 12
Exsisting Tenants
Tenant is added only on System form and only then it appears on the sysetm below
After the Delivery specialist added the system to the project and verify the system full configuration and confirm he can contineu and add the tenant
|  | Administrative | [6 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | TID | SID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T1 | S1234 | Account1 - the project account only |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T2 | S1235 | Account1 | [5 empty] | 12
Engagement circles
Read only - based on role list as now in QB
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Documents
Allocate a System

## Project form-Renewal-Standard
1. Sticky Title PID #1234 |  |  | PID P1235
2. Header |  |  | Project name | Project Type | Project sub type | Delivery date | Warranty/Service period (months) | Project status | Current milestone | Project Alers
|  |  | Free text | Read only - derived from opportuniy | Read only - derived from opportuniy | Editable - Date (Calendar) - derived from opportuniy | Read only - derived from opportuniy | Read only - Live/Done - based on tasks completion | Read only - from milestone list | Read only - auto generated base on predefined alerts: - Deliveryt date is missing - Delivery overdue
|  |  | Opportunity (name and ID) | Account (end user) | Region | Country | State | Time Zone | Time Group
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - auto generated by Country-Time Zone lookup table/formula | Read only - auto generated by lookup table
|  |  | Deal/Sale owner | Report to - direct | Report to - level 2
|  |  | Read only - derived from opportuniy | Read only - derived from organization chart | Read only - derived from organization chart
Available actions:
|  |  | Cancel project | Cancelation reason - mandatory *
3. Tenat requirements
Comments: | System and Teant Tab auto-update | System allocation comments
| The selected tenants and their systems for the standard renewal requirements , should automatically appear on the System and Tenant tab when the Project is created | To allocate the selected systems automatically to the system & tenant tab once the project is created
Standard renewal:
| Req ID | TID | SID
|  | T2 | S123
4. TABS | Milestones | Tasks | Systems and Tenants | Engagement circles | Documents
Milestones
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a milestone
Can create a new milstone
|  | A milestones status can be either: | Open - none of its tasks was completed
In progress - at least one but not all its tasks is completed
Done - all its tasks are completed
An indicator icon should be right to the milestones status
A progress bar should be displayed based on number of completed tasks
Order of milestones can be editted by permitted user only
Actions to support:
|  | Add milestone | Either from existing list or a new one
|  | Reset milestones (and tasks) | Set back the origianl milestones and their tasks according to the tempalte
The requested table and its fields:
Tasks
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a task
A task can creae only via a milestone - in a milestone form
|  | A task status can be either: | Open - none of its tasks was completed
Done - all its tasks are completed
An indicator icon should be right to the task status
Task status is update manually - by permitted user
Taks order is based by milestones order
Should be displayed as groups of of milestones
An option to set a dead line - a calendar type
|  | An option to set a dead line reminder in days | how many days beofore the deadline to generate alert
Alert - auto generaed upon either: over due or deadline reminder
|  | Ticket opening idicator/indication | Only for POC end - a ticket should be opened once "POC ended" taks is set as done and indicator should appear next to the task
Actions to support:
|  | Add Task | Only via a milestone form in the milestones tabs
The requested table and its fields:
Systems and Tenants
Existing System
List of added system after allocating them to the project with their current Cofiguration
Defautlt - empty list
Adding a system is done manually by the Delivery sepcialist
System allocation form - There should be two options: 1. To open and select only only Available POD/DEMO/Training systems list 2. To present and select only proudction system(s) that belong/in use by the current account of the project
Once the sysetm is allocated it appears on the Existing system list
|  | Administrative | [5 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | SID | PIDs (PID list) | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1234 | <all the PID the system is currently allocated to |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1235 | <all the PID the system is currently allocated to | [5 empty] | 12
Exsisting Tenants
Tenant is added only on System form and only then it appears on the sysetm below
After the Delivery specialist added the system to the project and verify the system full configuration and confirm he can contineu and add the tenant
|  | Administrative | [6 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | TID | SID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T1 | S1234 | Account1 - the project account only |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T2 | S1235 | Account1 | [5 empty] | 12
Engagement circles
Read only - based on role list as now in QB
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Documents
Allocate a System

## Project form-Renewal-Upsell
1. Sticky Title PID #1234 |  |  | PID P1235
2. Header |  |  | Project name | Project Type | Project sub type | Delivery date | Warranty/Service period (months) | Project status | Current milestone | Project Alers
|  |  | Free text | Read only - derived from opportuniy | Read only - derived from opportuniy | Editable - Date (Calendar) - derived from opportuniy | Read only - derived from opportuniy | Read only - Live/Done - based on tasks completion | Read only - from milestone list | Read only - auto generated base on predefined alerts: - Deliveryt date is missing - Delivery overdue
|  |  | Opportunity (name and ID) | Account (end user) | Region | Country | State
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy
|  |  | Deal/Sale owner | Report to - direct | Report to - level 2
|  |  | Read only - derived from opportuniy | Read only - derived from organization chart | Read only - derived from organization chart
Available actions:
3. Tenat requirements
|  |  | Cancel project | Cancelation reason - mandatory *
Must be filled in in case a projec is canceled
Comments: | Requirment types to display - generated base on opportuntiy | System and Teant Tab auto-update | System allocation comments
| The following requirement combination can be: 1. Change request requirements ONLY 2. BOTH - New and Change request requirements 3. BOTH - New requriements + Standard 4. BOTH - Change request requirements + Standard 5. THREE - New and Change request + Standard 6. Standard ONLY - in case of price upsell only without configuration change Maximum 3 types of requirement tables can be disaplyed | The selected tenants and their systems for either: - Change request requirment AND/OR; - Standard renewal requirment Should automatically appear on the System and Tenant tab when the Project is created | Change request requirements: to allocate the relevant systems & Tenant automatically to the system & tenant tab once the project is created New Tenant Requirement : In case of a request of an existing system, to allocate it automatically to the system & tenant tab once the project is created For standard renewal: To allocate the selected systems automatically to the system & tenant tab once the project is created
| New Tenant Requirements: | // Sales manager can ask a POC on existing customer's system |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Requirment ID | New System (Boolean) | SID (If not a new system) | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
|  | Yes/No |  | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
| Change request on existing tenant - FINAL CONFIGURATIOIN: |  |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Req ID | TID | SID | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
| Requirment ID | T2 | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
Standard renewal:
| Req ID | TID | SID
|  | T2 | S123
4. TABS | Milestones | Tasks | Systems and Tenants | Engagement circles | Documents
Milestones
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a milestone
Can create a new milstone
|  | A milestones status can be either: | Open - none of its tasks was completed
In progress - at least one but not all its tasks is completed
Done - all its tasks are completed
An indicator icon should be right to the milestones status
A progress bar should be displayed based on number of completed tasks
Order of milestones can be editted by permitted user only
Actions to support:
|  | Add milestone | Either from existing list or a new one
|  | Reset milestones (and tasks) | Set back the origianl milestones and their tasks according to the tempalte
The requested table and its fields:
Tasks
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a task
A task can creae only via a milestone - in a milestone form
|  | A task status can be either: | Open - none of its tasks was completed
Done - all its tasks are completed
An indicator icon should be right to the task status
Task status is update manually - by permitted user
Taks order is based by milestones order
Should be displayed as groups of of milestones
An option to set a dead line - a calendar type
|  | An option to set a dead line reminder in days | how many days beofore the deadline to generate alert
Alert - auto generaed upon either: over due or deadline reminder
|  | Ticket opening idicator/indication | Only for POC end - a ticket should be opened once "POC ended" taks is set as done and indicator should appear next to the task
Actions to support:
|  | Add Task | Only via a milestone form in the milestones tabs
The requested table and its fields:
Systems and Tenants
Existing System
List of added system after allocating them to the project with their current Cofiguration
Defautlt - empty list
Adding a system is done manually by the Delivery sepcialist
System allocation form - There should be two options: 1. To open and select only only Available POD/DEMO/Training systems list 2. To present and select only proudction system(s) that belong/in use by the current account of the project
Once the sysetm is allocated it appears on the Existing system list
|  | Administrative | [5 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | SID | PIDs (PID list) | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1234 | <all the PID the system is currently allocated to |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1235 | <all the PID the system is currently allocated to | [5 empty] | 12
Exsisting Tenants
Tenant is added only on System form and only then it appears on the sysetm below
After the Delivery specialist added the system to the project and verify the system full configuration and confirm he can contineu and add the tenant
|  | Administrative | [6 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | TID | SID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T1 | S1234 | Account1 - the project account only |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T2 | S1235 | Account1 | [5 empty] | 12
Engagement circles
Read only - based on role list as now in QB
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Documents
Allocate a System

## Project form-Renewal-Down Sell
1. Sticky Title PID #1234 |  |  | PID P1235
2. Header |  |  | Project name | Project Type | Project sub type | Delivery date | Warranty/Service period (months) | Project status | Current milestone | Project Alers
|  |  | Free text | Read only - derived from opportuniy | Read only - derived from opportuniy | Editable - Date (Calendar) - derived from opportuniy | Read only - derived from opportuniy | Read only - Live/Done - based on tasks completion | Read only - from milestone list | Read only - auto generated base on predefined alerts: - Deliveryt date is missing - Delivery overdue
|  |  | Opportunity (name and ID) | Account (end user) | Region | Country | State
|  |  | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy | Read only - derived from opportuniy
|  |  | Deal/Sale owner | Report to - direct | Report to - level 2
|  |  | Read only - derived from opportuniy | Read only - derived from organization chart | Read only - derived from organization chart
Available actions:
3. Tenat requirements
|  |  | Cancel project | Cancelation reason - mandatory *
| Requirment types to display - generated base on opportuntiy | System and Teant Tab auto-update |  | Must be filled in in case a projec is canceled
| The following requirement combinations can be: 1. Change request requirements ONLY 2. BOTH - Change request requirements + Standard 3. Standard ONLY - in case of price down sell withotut configuration change Maximum 2 types of requirement tables can be disaplyed | The selected tenants and their systems for either: - Change request requirment AND/OR; - Standard renewal requirment Should automatically appear on the System and Tenant tab when the Project is created
| Change request on existing tenant - FINAL CONFIGURATIOIN: |  |  | Environment |  | Core Details | [13 empty] | Modules | [5 empty] | API |  |  | AI | Additional features
| Req ID | TID | SID | Hosting | Cloud Platfrom | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Tangles Go | Webloc | Webeye | Ingest | Blockchain | Cross System | Enalbe | Daily Qty | Monthly
| Requirment ID | T2 | S123 | Saas On premise Hybrid | Local Azure AWS Customer's VPC Azure Gov | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Weaver Dark web Lynx | Yes/No | Integer | Integer | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
Standard renewal:
| Req ID | TID | SID
|  | T2 | S123
4. TABS | Milestones | Tasks | Systems and Tenants | Engagement circles | Documents
Milestones
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a milestone
Can create a new milstone
|  | A milestones status can be either: | Open - none of its tasks was completed
In progress - at least one but not all its tasks is completed
Done - all its tasks are completed
An indicator icon should be right to the milestones status
A progress bar should be displayed based on number of completed tasks
Order of milestones can be editted by permitted user only
Actions to support:
|  | Add milestone | Either from existing list or a new one
|  | Reset milestones (and tasks) | Set back the origianl milestones and their tasks according to the tempalte
The requested table and its fields:
Tasks
Based on Template - see Milestones and Tasks Template sheet
Inline edtiable table
Can add/edit/remove/rename a task
A task can creae only via a milestone - in a milestone form
|  | A task status can be either: | Open - none of its tasks was completed
Done - all its tasks are completed
An indicator icon should be right to the task status
Task status is update manually - by permitted user
Taks order is based by milestones order
Should be displayed as groups of of milestones
An option to set a dead line - a calendar type
|  | An option to set a dead line reminder in days | how many days beofore the deadline to generate alert
Alert - auto generaed upon either: over due or deadline reminder
|  | Ticket opening idicator/indication | Only for POC end - a ticket should be opened once "POC ended" taks is set as done and indicator should appear next to the task
Actions to support:
|  | Add Task | Only via a milestone form in the milestones tabs
The requested table and its fields:
Systems and Tenants
Existing System
List of added system after allocating them to the project with their current Cofiguration
Defautlt - empty list
Adding a system is done manually by the Delivery sepcialist
System allocation form - There should be two options: 1. To open and select only only Available POD/DEMO/Training systems list 2. To present and select only proudction system(s) that belong/in use by the current account of the project
Once the sysetm is allocated it appears on the Existing system list
|  | Administrative | [5 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | SID | PIDs (PID list) | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1234 | <all the PID the system is currently allocated to |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | S1235 | <all the PID the system is currently allocated to | [5 empty] | 12
Exsisting Tenants
Tenant is added only on System form and only then it appears on the sysetm below
After the Delivery specialist added the system to the project and verify the system full configuration and confirm he can contineu and add the tenant
|  | Administrative | [6 empty] | Core Details | [15 empty] | Modules |  |  |  | AI | Additional features
|  | Actions | TID | SID | Account | Country | Time group | Operational status | Product | Licenses | Users | Con. Searches | Daily Qty Searches | Monthly Qty Searches | Con. Analyses | Daily Qty Analyses | Monthly Qty Analyses | Topic analyses | Std. Monitors | Full monitors | Topic monitors | Map Center | Weloc | Webeye | Tangles Go | Ingest | Blockchain | Cross system
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T1 | S1234 | Account1 - the project account only |  |  |  | Tangles | Integer | 28 | Integer | Integer | Integer | Integer | Integer | Integer | Picklist-Single select: Yes/No | Integer | Integer | Integer | Picklist-Single select + "Add new" | Integer | Integer | Integer | Integer | Integer | Picklist-Multi select: Dark web/Lynx | Picklist-Multi select:: Face Detection OCR Object Detection Reverse Face Landmark Video Analysis CoAnalyst | Picklist-Multi select: SSO 2FA Export to PDF Enhanced Search Post Translation
|  | Delete/Edit/Move(to a differnet system/project) - for permitted users only | T2 | S1235 | Account1 | [5 empty] | 12
Engagement circles
Read only - based on role list as now in QB
There should be different set of engagement circles. For now, the most important circle is the list of roles that need to be notified upon tenant (system actually) upgrade named “Send version update email” or any similar name.
The list should contain SF user names based on roles. In that case changing users per role will be transparent and auto-updated on the list
Each circle should be presented in a separated line (could be a grid where first column is the circle subject and the second column is the list)
Documents
Allocate a System

## Dashboards
Inline functionalities all dashboards should support:
Counter at the top of the page of all items
Sort A-Z, Z-A | Per column
Filtering: | By column
Filter values will not be a free text but a pick-list based on the existing values in the column
Number of filter fields should be dynamic derived from the number of columns
Group by A-Z, Z-A | Per column
A summary per group - counting of each group per column
Search | Built-in search on entire table cells – free text: search results filter the table and display only the lines where the searched string appears.
In some dashboards – replace all (similar to CTRL+H in Office) for textual fields
Creating a new dashboard based on the default dashboard layouts – need to find a solution
Add/hide column
No one should be permitted to change the default dashboard layouts
1- Projects - deliveries(sales) and POC
As it appears today in QB
Progress bar indicator
Alerts - due dates
2- Production Repository
As it appears today in QB
3- Systems Customers and POC projects
All sysetems that have ever assinged to a delivery project OR a POC project, no matter their operational status should be included in this dashboard
POC/DEMO/Training systems that were assigned to a POC project ("copied/pasted") must appear on this dashbaord, even if they were set as OBSOLETE on the POC/DEMO/Training pool.
The same structure as today in QB with some adjustments e.g. warranty is irrelevant, need to add tenant list
Additional fields: <list of TIDs), MID (machine ID
Columns to remove - all warranty fields
4- Tenants Customers and POC projects
Similar to 3- Systems Customers and POC projects with one differnece - main key TID and not SID, warranty columns (initial, start/end date, status etc.) shold appear in this dashboard
5- POC/DEMO/Training inventory
5- Infrastructure

## Ececutive Reports
Todays' QB Delivery and POC reports